## Legend
Legend & Instructions
Tabs
Tab | What's inside
Legend & Instructions | This page.
Developer checklist | One sheet per user (01–12) plus 13 BTS, listing every feature for that user.
Non-development checklist | Forms, surveys, testing, writing, training, and services to set up.
Checkboxes
Box | Who ticks it | Tick when…
Built | Developer | It works and is merged to the main branch.
Tested | QA | It passed the test in the QA run.
Matches QA | QA | It matches the paper and the Figma frame.
Done | Owner | The non-development task is finished.
Columns
Column | Meaning
Frame | The Figma frame to copy (e.g. S-03b, M-10, PWA-04).
Dev | Who is building it.
Remarks | Short notes: what's missing, bug found, PR link, "blocked by…".
Rules
• Developers: update your rows after every merge.
• QA: test anything with Built ticked and Tested empty; write problems in Remarks.
• A feature is done only when all three boxes are ticked.
Filled 30 Oct 2026 from the dev branch: "Built" = works on dev (not yet merged to main). Remarks say how it was checked: "Auto-test" = Vitest suite (302 passing), "App" = walked in the app. Tested and Matches QA are left for QA.

## 01 Student
# | Feature | Frame | Dev | Built | Tested | Matches QA | Remarks
1 | Register with @student.hau.edu.ph only | S-01 |  | TRUE | FALSE | FALSE | Works. Only @student.hau.edu.ph / @hau.edu.ph accepted; look-alike domains and duplicates rejected. Auto-test: admin, services.
2 | Verify email by link, then log in | S-16, S-00 |  | TRUE | FALSE | FALSE | Works: verification email (dev outbox locally, Firebase Auth link on Firebase), then the Sys Admin activates the account (flag ACCOUNT_ACTIVATION). Auto-test: admin, services.
3 | Reset password | S-00 |  | TRUE | FALSE | FALSE | Firebase build: Firebase Auth reset email. Local build only sends a mock email to the outbox (no new-password screen there). No automated test.
4 | Dashboard: trail, stats, returned alert | S-02 |  | TRUE | FALSE | FALSE | Trail, stat tiles, "waiting on your group" and returned/overdue alerts. Auto-test: student. App: checked 30 Oct.
5 | My Project page | S-03 |  | TRUE | FALSE | FALSE | Works. Auto-test: student.
6 | Submit / resubmit PDF (stage auto) | S-03b |  | TRUE | FALSE | FALSE | PDF only, max 25 MB, real-PDF byte check, progress + cancel; the stage decides the document type; a re-upload is a new version. Auto-test: student, uploads.
7 | Version history (read-only) | S-04 |  | TRUE | FALSE | FALSE | All versions kept and readable; superseded ones marked. Auto-test: student (T13), services.
8 | Read feedback & annotations | S-05 |  | TRUE | FALSE | FALSE | Reviewer decisions + pinned annotations; panel private notes reach the group only after the verdict. Auto-test: student, annotations.
9 | Weekly logs: upload filled FM-AAC-SOC-2003 | S-06, F-01 |  | TRUE | FALSE | FALSE | REBUILT 30 Oct: download blank FM-2003, upload the filled form (PDF/JPG/PNG), adviser marks reviewed or returns. Auto-test: student, signedForms. App: checked.
10 | View verdict, download revision form | F-03 |  | TRUE | FALSE | FALSE | NEW 30 Oct: Defense tab shows verdict, required revisions, countdown and the Panel Chair's uploaded FM-2004 (View / Download). App: checked as a student.
11 | Final requirements upload | S-03c |  | TRUE | FALSE | FALSE | Editor's + Plagiarism certificates and final manuscript at Final Requirements; URO return re-upload. Auto-test: student, uro.
12 | Capstone 2 unlocks after Approved Revisions | S-02 |  | TRUE | FALSE | FALSE | After FM-2004 is complete, Instructor 1 routes the group to Capstone 2 (a click, not automatic — S5.8). Auto-test: instructor1, handoff.

## 02 Adviser
# | Feature | Frame | Dev | Built | Tested | Matches QA | Remarks
1 | Dashboard | DB-10 |  | TRUE | FALSE | FALSE | Works, incl. red overdue tile. Auto-test: adviser, workspaces.
2 | My Advisees hub | S-07b |  | TRUE | FALSE | FALSE | Works (/advisees).
3 | Group page with 3 tabs | S-07c–e |  | TRUE | FALSE | FALSE | DIFFERS FROM FIGMA: advisers use the shared project page tabs (Overview, Documents, Weekly logs, Defense, Forms, History), not the 3-tab page of S-07c–e. Same actions are available.
4 | Review: read, highlight, comment | M-10 |  | TRUE | FALSE | FALSE | PDF viewer: select words or mark an area, add a comment; the file is never changed. Auto-test: annotations.
5 | Approve or return with remarks | M-11 |  | TRUE | FALSE | FALSE | Works. Note: decisions are Approve / Minor / Major / Reject (Figma shows only approve or return). Auto-test: adviser (T17).
6 | Weekly logs: mark reviewed / return | S-09, M-12, M-13 |  | TRUE | FALSE | FALSE | REBUILT 30 Oct: "Mark as reviewed" / "Return to preparer" (remarks required) on uploaded FM-2003. Auto-test: adviser, services. App: checked.
7 | Defense clearance + upload FM-AAC-SOC-2005 | S-07d, F-05, F-06 |  | TRUE | FALSE | FALSE | REBUILT 30 Oct: choose Recommended / Not Recommended (reasons), upload the signed FM-2005; Not Recommended keeps the group in Implementation. Auto-test: signedForms.
8 | Revision verification (before panel) | S-07e |  | TRUE | FALSE | FALSE | Approve the revised manuscript, then "Verify the revisions" on the Forms tab (no upload). Auto-test: adviser, panel. App: checked.
9 | Version history per group | S-04b |  | TRUE | FALSE | FALSE | Works (/versions).
10 | Overdue revisions counter (red) | DB-10 |  | TRUE | FALSE | FALSE | Red "Overdue revisions" tile; overdue job runs hourly (Firebase) or from Dev tools. Auto-test: chair + services (T18).

## 03 Instructor1
# | Feature | Frame | Dev | Built | Tested | Matches QA | Remarks
1 | Dashboard | DB-08 |  | TRUE | FALSE | FALSE | Works. Auto-test: instructor1.
2 | Create groups, lock roster | S-22 |  | FALSE | FALSE | FALSE | Creating groups (4 per group, one group per student) works — auto-test: instructor1. MISSING: the "Lock rosters" control from S-22.
3 | Send groups to Program Chair | S-22 |  | TRUE | FALSE | FALSE | Works: "Forward roster to the Program Chair/Coordinator". Auto-test: instructor1, handoff.
4 | Group page: status, locked until adviser reviews | S-23c |  | FALSE | FALSE | FALSE | Trail and status work. MISSING: the newest draft is not locked for Instructor 1 until the adviser reviews it (S-23c).
5 | Check submission → checked / return | M-14, M-15 |  | FALSE | FALSE | FALSE | Instructor 1 can return drafts (remarks) and decides at Topic Proposal. MISSING: a "Checked" decision on drafts at Proposal Development (WORKFLOWS S4.2 gives approval to the Adviser).
6 | Topic decision & working title | S-23b |  | TRUE | FALSE | FALSE | Approve one of the five topics, register it as the title. Auto-test: instructor1.
7 | Defended groups → forward titles | S-23d |  | FALSE | FALSE | FALSE | Defended Groups page lists them. MISSING: the "Forward titles to Program Chair" action (S-23d).
8 | Version history (newest after adviser) | S-04d |  | FALSE | FALSE | FALSE | Version history works. MISSING: the newest-version lock until the adviser reviews it (S-04d).

## 04 Instructor2
# | Feature | Frame | Dev | Built | Tested | Matches QA | Remarks
1 | Dashboard | DB-09 |  | TRUE | FALSE | FALSE | Works. Auto-test: instructor2.
2 | Rosters & Scheduling (all C2 groups) | S-24 |  | TRUE | FALSE | FALSE | Works (/scheduling).
3 | Schedule the final oral defense | S-24 |  | TRUE | FALSE | FALSE | Only after the Program Chair endorses (T7). Auto-test: instructor2.
4 | Update group status + status log | S-24b |  | FALSE | FALSE | FALSE | Instructor 2 confirms milestones, readiness and post-defense requirements. MISSING: "Update group status" (Active / On hold) with a status log (S-24b).

## 05 Program Chairs
# | Feature | Frame | Dev | Built | Tested | Matches QA | Remarks
1 | Dashboard: all program projects, filter, export | S-12 |  | TRUE | FALSE | FALSE | NEW 30 Oct: "All projects in your programs" table with search, stage/block filters and Export. App: checked.
2 | Assignments & Routing hub (pending action per project) | S-13a |  | TRUE | FALSE | FALSE | Works (/routing). Auto-test: programchair.
3 | Assign adviser (load, conflicts) → routes to Assoc. Dean | M-24 |  | TRUE | FALSE | FALSE | Conflicts blocked in the picker (adviser cannot sit on own panel). Routes to Dean + AD (both, any order). Check in QA that adviser load counts show in the picker.
4 | Assign panel (adviser excluded) | M-25 |  | TRUE | FALSE | FALSE | Adviser excluded (T19). Auto-test: programchair.
5 | Endorse final defense + upload noted FM-AAC-SOC-2005 | M-20, M-21 |  | TRUE | FALSE | FALSE | REBUILT 30 Oct: download the adviser's FM-2005, sign "Noted by", upload the noted copy, endorse. MISSING: "Return to preparer" (M-21). Auto-test: signedForms.
6 | Clearance routing to URO | M-22, M-23 |  | TRUE | FALSE | FALSE | REBUILT 30 Oct: upload the signed Approval Sheet and route to URO. MISSING: "Return to preparer" (M-23). Auto-test: programchair, signedForms.
7 | Version history module | S-04c |  | TRUE | FALSE | FALSE | Works (/versions).

## 06 Associate Dean
# | Feature | Frame | Dev | Built | Tested | Matches QA | Remarks
1 | Dashboard | DB-03 |  | TRUE | FALSE | FALSE | Works. Auto-test: dean.
2 | Executive approvals queue | S-21b |  | TRUE | FALSE | FALSE | Works (/approvals, /adviser-approvals).
3 | Adviser routing slip: approve & forward / return | M-03, M-04 |  | FALSE | FALSE | FALSE | Approve works (both offices, any order; NEW-5 conflict rule). MISSING: return to the Program Chair.
4 | Schedule the Proposal Defense | S-21 |  | FALSE | FALSE | FALSE | NOT BUILT AS IN FIGMA: the Program Chair schedules the proposal defense (flag PROPOSAL_DEFENSE_SCHEDULER, a mockup default). Team must decide who schedules (paper Table 1).

## 07 Dean
# | Feature | Frame | Dev | Built | Tested | Matches QA | Remarks
1 | Dashboard | DB-02 |  | TRUE | FALSE | FALSE | Works. Auto-test: dean.
2 | Executive approvals queue | S-19 |  | TRUE | FALSE | FALSE | Works.
3 | Adviser routing slip: approve / return | M-01, M-02 |  | FALSE | FALSE | FALSE | Approve works (both offices, any order). MISSING: return to the Program Chair.
4 | Final signature: upload signed Approval Sheet | M-05, M-06 |  | TRUE | FALSE | FALSE | REBUILT 30 Oct: download the latest Approval Sheet, sign outside, upload it; the second executive upload archives the project. MISSING: "Return to preparer" (M-06). Auto-test: dean, signedForms.
5 | Student Capstone/Thesis list (search, filter) | S-20 |  | TRUE | FALSE | FALSE | NEW 30 Oct: all projects with search, program/stage/block filters and Export (Student Capstone/Thesis page).
6 | Export tables (Excel / PDF / Word) | S-18 |  | TRUE | FALSE | FALSE | NEW 30 Oct: Excel (.xlsx) and Word (.docx) generated in the browser, PDF via the print dialog. On Reports, Archive and the PC/Dean project lists — not on every table yet. Exports are not audit-logged.

## 08 URO
# | Feature | Frame | Dev | Built | Tested | Matches QA | Remarks
1 | Dashboard | DB-11 |  | TRUE | FALSE | FALSE | Works. Auto-test: uro.
2 | Clearance queue | S-25 |  | TRUE | FALSE | FALSE | Works. Auto-test: uro (T12).
3 | 3-step clearance → approve / return to group | M-07, M-08, M-09 |  | TRUE | FALSE | FALSE | Verify certificates + manuscript, approve, or return chosen items with remarks. DIFFERS FROM FIGMA: one screen, not a 3-step dialog. Auto-test: uro.

## 09 Panel Member
# | Feature | Frame | Dev | Built | Tested | Matches QA | Remarks
1 | Dashboard (only Dashboard + Assigned Panels in sidebar) | DB-06 |  | TRUE | FALSE | FALSE | Works. Note: every account now also has Archive and Blank forms in the sidebar.
2 | Assigned panels list | S-15a |  | TRUE | FALSE | FALSE | Works (/panels). Latest version only (T15).
3 | Manuscript viewer + private comments | S-10 |  | TRUE | FALSE | FALSE | Private notes are the author's alone until the verdict (T4). Auto-test: panel, annotations.
4 | AI summary panel (summary only, cautions) | S-10 |  | TRUE | FALSE | FALSE | Shown to Adviser + panel (flag AI_SUMMARY_AUDIENCE) with the AI label. Gemini runs only with a browser API key; on the server it still writes placeholder text.
5 | Verify revisions: confirm / not yet (private note) | M-16, M-17 |  | TRUE | FALSE | FALSE | NEW 30 Oct: check each required revision (Addressed / Not addressed), then "Confirm revisions" or "Save as not yet confirmed" with a private note. Auto-test: panel. App: checked.

## 10 Panel Chair
# | Feature | Frame | Dev | Built | Tested | Matches QA | Remarks
1 | Dashboard | DB-07 |  | TRUE | FALSE | FALSE | Works.
2 | Group page: actions inside the group | S-15 |  | TRUE | FALSE | FALSE | Works.
3 | Review panel comments | M-18 |  | TRUE | FALSE | FALSE | NEW 30 Oct (partial): before the verdict, shows each panelist and how many shared comments they left. Private notes stay private.
4 | Record verdict (Minor / Major / Change Topic) | M-19 |  | TRUE | FALSE | FALSE | Works. DIFFERS FROM FIGMA: verdict names are "Passed with Minor/Major Revisions" and "Re-defense", not "Approved with…" / "Change Topic" (flag VERDICT_VALUES). Auto-test: chair.
5 | Download blank FM-AAC-SOC-2004, upload signed copy | E-00, E-01 |  | TRUE | FALSE | FALSE | REBUILT 30 Oct: verdict needs the FM-2004 signed by chair + proponents; after members confirm, the chair uploads the final copy, which completes revisions. Auto-test: chair, panel. App: checked.

## 11 System Administrator
# | Feature | Frame | Dev | Built | Tested | Matches QA | Remarks
1 | Dashboard | DB-05 |  | TRUE | FALSE | FALSE | Works.
2 | User accounts: search, filter | S-26 |  | TRUE | FALSE | FALSE | Works. Auto-test: admin.
3 | Assign roles to new accounts | S-26 |  | TRUE | FALSE | FALSE | Works. Auto-test: admin.
4 | Deactivate accounts | S-26 |  | TRUE | FALSE | FALSE | Works. Auto-test: admin.
5 | Role configuration (read-only academic columns, Override) | S-27 |  | TRUE | FALSE | FALSE | Works incl. deny-only permission overrides. Auto-test: admin.

## 12 Shared (All users)
# | Feature | Frame | Dev | Built | Tested | Matches QA | Remarks
1 | Register with an @hau.edu.ph or @student.hau.edu.ph email; any other domain is rejected | S-01 |  | TRUE | FALSE | FALSE | Works. Auto-test: guard, admin.
2 | Verify email by link | S-16 |  | TRUE | FALSE | FALSE | Works.
3 | Log in with institutional email and password | S-00 |  | TRUE | FALSE | FALSE | Firebase build: Firebase Auth. Local build: dev persona panel.
4 | Reset password | S-00 |  | TRUE | FALSE | FALSE | See 01 Student #3.
5 | "Acting as" switcher (global + project roles) | Role switcher |  | TRUE | FALSE | FALSE | Works. Auto-test: workspaces.
6 | Archive: search and filter | S-17 |  | TRUE | FALSE | FALSE | NEW 30 Oct: every signed-in account browses archived projects as metadata only (title, members, program, adviser, year); Dean/AD/Admin keep the full records. Seed has no archived project to show.
7 | Download blank forms | E-00, F-10 |  | TRUE | FALSE | FALSE | NEW 30 Oct: Blank form library (/forms) + "Download blank" on every form step. PDF only — the DOCX download in E-00 is not provided. App: all 4 PDFs download.
8 | Upload signed form (one method per form) | E-01 |  | TRUE | FALSE | FALSE | NEW 30 Oct: download latest copy → sign outside → upload (PDF/JPG/PNG) + 3 "before you submit" checks. "One method per form" is a reminder; the system cannot detect it. Auto-test: signedForms, rules-tests.
9 | Uploaded form viewer (read-only) | F-02, F-04, F-07, F-09 |  | TRUE | FALSE | FALSE | NEW 30 Oct: every uploaded copy has View / Download (Forms tab, Defense record, Weekly logs). Opens the file itself, not the styled F-02/F-04 page.
10 | Email for every workflow event | — |  | TRUE | FALSE | FALSE | Every event writes an email to the outbox (dev). Real sending (Resend) is written but not deployed.
11 | Install app: Android prompt, iPhone steps, in-app browsers | PWA-01–07 |  | TRUE | FALSE | FALSE | Auto-test: browserSupport. Needs a real-phone check.
12 | Device notifications: switch, permission, test | PWA-09–11 |  | TRUE | FALSE | FALSE | Works while the app is open; real push needs the Blaze plan + VAPID key (not deployed).
13 | Sign-out removes the device token | PWA-11 |  | TRUE | FALSE | FALSE | Code path done (unregisterPushToken on sign-out); only matters once push is deployed.
14 | Lock screen shows neutral text only | PWA-12 |  | TRUE | FALSE | FALSE | Auto-test: deviceNotice.
15 | "New version ready · Reload" banner | PWA-13 |  | TRUE | FALSE | FALSE | Works in the PWA build (capstone-pwa-preview). Not re-checked 30 Oct.
16 | Phone / portrait tablet: view-only | 06 · Responsive |  | TRUE | FALSE | FALSE | Auto-test: viewOnly.
17 | Landscape tablet: full functions | 06 · Responsive |  | TRUE | FALSE | FALSE | Auto-test: viewOnly.

## 13 BTS
# | Feature | Paper | Dev | Built | Tested | Matches QA | Remarks
1 | Access rules on the server (Firestore rules + Cloud Functions) | p. 4 |  | TRUE | FALSE | FALSE | firestore.rules + storage.rules + the act Cloud Function; emulator tests pass (test:rules 20/20, test:act). NOT deployed to the live project.
2 | Versions never overwritten; numbered per stage | p. 50 |  | TRUE | FALSE | FALSE | Never overwritten (auto-test T13). Numbered per document type, which mostly matches "per stage".
3 | Upload checks: PDF only, size limit, progress | p. 55 |  | TRUE | FALSE | FALSE | Auto-test: uploads, student, rules-tests.
4 | Trail moves and date-stamps after each approval | p. 51 |  | TRUE | FALSE | FALSE | Auto-test: services (T21), handoff.
5 | Revision countdown + overdue flag | p. 53 |  | TRUE | FALSE | FALSE | Auto-test: chair + services (T18).
6 | One notification record → email (Resend) + push (FCM) | p. 67 |  | FALSE | FALSE | FALSE | Written (functions/index.js deliverOutbox); runs on the emulators without sending. Not deployed: needs Blaze, RESEND_API_KEY, VAPID key.
7 | Gemini summary once per version, paid tier, AI label | p. 55 |  | FALSE | FALSE | FALSE | Generated when the defense schedule is published, with the AI label. Server still writes placeholder text (no key there); "paid tier" is an account task.
8 | Audit log nobody can edit | p. 51 |  | TRUE | FALSE | FALSE | Append-only; rules deny every client write. Auto-test: services (T21).
9 | Pages load in under 3 seconds | p. 55 |  | FALSE | FALSE | FALSE | Not measured.
10 | HTTPS, session timeout, input validation | p. 55 |  | FALSE | FALSE | FALSE | Input validation done (uploads, forms, emails). HTTPS comes with Firebase Hosting (not deployed). MISSING: session timeout.
11 | Scheduled backups | p. 55 |  | FALSE | FALSE | FALSE | Not built.
12 | Firebase Hosting + domain + SSL | p. 73 |  | FALSE | FALSE | FALSE | firebase.json has a hosting config; not deployed, no domain yet.
13 | Pull-request reviews + GitHub Actions deploy | p. 70 |  | FALSE | FALSE | FALSE | No .github workflows in the repo yet.
14 | Firebase Emulator tests for rules and functions | p. 71 |  | TRUE | FALSE | FALSE | npm run test:rules, test:act, test:triggers (Docker). Passed 30 Oct.
15 | Accessibility basics (WCAG 2.2) | p. 65 |  | FALSE | FALSE | FALSE | Labels, focus rings, contrast tokens, keyboard use are in place; no formal WCAG 2.2 audit yet.
16 | Push works with the app closed (Blaze plan) | p. 29 |  | FALSE | FALSE | FALSE | Written (sw-notify.js + FCM), not deployed (Blaze).
Behind the scenes: things no single user sees, but every screen depends on.

## NonDevChecklist
Non-development checklist
Everything besides coding that the paper says we will do, plus capstone requirements. Page numbers are from the revised manuscript.
Testing instruments
Task | Paper | Who | Due | Done | Remarks
Finalize the functional testing checklist (Appendix J) from the final features | p. 78 |  |  | FALSE
Adviser checks the checklist (content validity); keep the approval | p. 78 |  |  | FALSE
Pilot test the checklist with a few respondents | p. 78 |  |  | FALSE
Google Form: functional checklist | p. 81 |  |  | FALSE
Google Form: SUS, unmodified (Appendix L) | p. 78 |  |  | FALSE
Google Form: TAM, adapted wording (Appendix N) | p. 79 |  |  | FALSE
Google Form: ISO/IEC 25010 expert form (Appendix O) | p. 79 |  |  | FALSE
Data gathering
Task | Paper | Who | Due | Done | Remarks
Cover letter to host/locale signed (Appendix A) | p. 36 |  |  | FALSE
Institutional approvals before testing | p. 89 |  |  | FALSE
Invitation letters to respondents | p. 81 |  |  | FALSE
Informed consent form | p. 81 |  |  | FALSE
Demo video of the system (shown before testing) | p. 81 |  |  | FALSE
Test accounts with dummy data for every role | p. 77 |  |  | FALSE | Local/emulator demo data covers every role (§6 personas + NPC groups; Dev tools scenarios T1–T21). The live Firebase project is empty.
Respondent list: 264 students, 35 faculty, 1 URO, IT experts | pp. 75–77 |  |  | FALSE
Testing schedule (labs, offices, or online) | p. 77 |  |  | FALSE
Participant codes and password-protected storage | p. 90 |  |  | FALSE
Analysis and writing
Task | Paper | Who | Due | Done | Remarks
Analyze results (Pass/Fail, SUS, TAM, ISO/IEC 25010) | p. 82 |  |  | FALSE
Write Chapter 4: Results and Discussion | — |  |  | FALSE
Write Chapter 5: Conclusion and Recommendations | — |  |  | FALSE
Paper updates
Task | Paper | Who | Due | Done | Remarks
Table 1: remove "compare versions" | p. 51 |  |  | FALSE | System has no compare-versions feature (matches).
Table 1: weekly logs are uploaded, not signed in the system | p. 52 |  |  | FALSE | System now matches (30 Oct): weekly logs are uploaded files the adviser reviews.
Table 1: forms are signed outside the system and uploaded | p. 53 |  |  | FALSE | System now matches (30 Oct): every form is signed outside and uploaded.
Table 1: "report generation" → export from tables (or keep a report) | p. 53 |  |  | FALSE | System has Reports + Export (Excel/PDF/Word) on tables.
Table 1: clearance by URO, Program Chair and Dean | p. 53 |  |  | FALSE
Table 1: who schedules each defense | p. 52 |  |  | FALSE | System today: Program Chair schedules the proposal defense, Instructor 2 the final. Figma S-21 says Associate Dean — decide and tell the devs.
Update the Table of Contents page numbers | pp. 1–3 |  |  | FALSE
Update appendices D–J to the final system | Appendices |  |  | FALSE
Replace or justify Kayes (2018), Larman & Basili (2003), Tómasdóttir (2020) | References |  |  | FALSE
Rollout and handover
Task | Paper | Who | Due | Done | Remarks
Pilot test of the system by the group | p. 74 |  |  | FALSE
Training for advisers and panelists (online reviews and clearances) | p. 74 |  |  | FALSE
Quick user guide per role, for the training (suggested) | p. 74 |  |  | FALSE
Maintenance notes for the SOC system administrator (suggested) | p. 74 |  |  | FALSE
Accounts and services
Task | Paper | Who | Due | Done | Remarks
Buy the domain hausoc-research.org (Hostinger) | p. 73 |  |  | FALSE
Firebase Blaze plan and billing | pp. 29, 72 |  |  | FALSE | Needed for: Cloud Functions (act, emails, push), scheduled overdue check.
Gemini API on a paid tier | p. 54 |  |  | FALSE | Needed for: AI summaries on the server.
Resend account and verified sending domain | p. 62 |  |  | FALSE | Needed for: real emails (deliverOutbox).
Web Push key pair for Firebase Cloud Messaging | — |  |  | FALSE | Needed for: push with the app closed.
Capstone requirements
Task | Paper | Who | Due | Done | Remarks
Weekly log FM-AAC-SOC-2003 after every consultation | p. 38 |  |  | FALSE
Signed FM-AAC-SOC-2004 and proposal revision form submitted | p. 37 |  |  | FALSE
FM-AAC-SOC-2005 adviser recommendation before the final defense | — |  |  | FALSE
English editing → Editor's Certificate | p. 38 |  |  | FALSE
Plagiarism and AI check → Plagiarism Clearance Certificate | p. 38 |  |  | FALSE
Approval Sheet signatures | p. 38 |  |  | FALSE
Final defense slides and live demo | — |  |  | FALSE